JANE.M DESIGNS

Fashion Brand Turnaround Playbook

90-day strategy, operating model, campaigns, pricing, sales process and execution tracker

Turnaround thesis Jane.M must move from a talent-led creative presence to a commercially disciplined fashion business: clear offers, visible prices, WhatsApp sales office, proof, campaign rhythm, deposits and weekly KPI control.

# 1. Strategic objective

In 90 days, convert Jane.M from a content-led fashion page into a visible, trusted, order-generating women’s apparel business with clear offers, repeatable campaigns and predictable weekly sales activity.

| Metric | 90-day target |
| --- | --- |
| Qualified inquiries | 20-40 per week |
| Paid orders | 5-10 per week |
| Quote-to-deposit conversion | 30%+ |
| Average order value | M900+ |
| Late deliveries | 0 |
| Referral orders | 2+ per week |

# 2. Positioning

Brand promise Elegant, feminine, made-to-measure outfits for Basotho women who want to look special without looking ordinary.

| Brand lane | Meaning |
| --- | --- |
| Elegant | Premium finish and graceful silhouettes, not random sewing. |
| Feminine | Designs that make women feel beautiful and confident. |
| Event-ready | Graduations, weddings, church, work events and bridal parties. |
| Custom but accessible | Made-to-measure, but packaged into clear tiers and lead times. |

# 3. Offer architecture

| Signature line | Target customer | Commercial role |
| --- | --- | --- |
| Graduation Belle | Graduates and families | Immediate campaign opportunity |
| Wedding Guest Queen | Women attending weddings/lobola | High-volume seasonal line |
| Sunday Best / Church Lady | Church and event women | Stable monthly orders |
| Office Elegance Set | Professional women | Repeatable capsule line |
| Seshoeshoe Modern Muse | Heritage-conscious buyers | Differentiation line |

# 4. Pricing and deposits

| Tier | Price range | Includes |
| --- | --- | --- |
| Simple | M450-M750 | Standard fabric, clean finish, limited changes |
| Premium | M800-M1,500 | Better fabric, lining, fitting and detail |
| Luxe | M1,800-M4,500+ | Statement pieces, priority production, premium finish |
| Ready-to-wear | M250-M650 | Pre-made, no custom changes |

| Order type | Deposit policy |
| --- | --- |
| Normal custom | 60% deposit, balance before collection |
| Rush order | 80% deposit, balance before collection |
| Bridal/group | 50% deposit, 30% after fitting, 20% before delivery |
| Ready-to-wear | 100% upfront |

# 5. Target market priorities

| Segment | Need | Message |
| --- | --- | --- |
| Graduates | Unique and memorable look | Your graduation look should be remembered. |
| Wedding guests | Stand out respectfully | Never basic at a wedding. |
| Bridesmaids | Coordinated looks and deadline control | Beautiful bridal party looks without stress. |
| Church women | Modest elegance | Elegant outfits for women of grace. |
| Professional women | Polished wardrobe | Workwear that still feels feminine. |
| Diaspora Basotho | Cultural-modern pieces | Modern Basotho elegance, wherever you are. |

# 6. Sales funnel and WhatsApp operating model

The buying path should be simple: Content -> Inquiry -> Catalogue -> Quote -> Deposit -> Measurements -> Fitting -> Delivery -> Testimonial -> Referral.

| WhatsApp feature | Configuration |
| --- | --- |
| Catalogue | Signature pieces with price-from ranges |
| Quick replies | Pricing, lead time, measurements, deposit policy |
| Labels | New lead, quoted, deposit paid, production, fitting, collected |
| Auto greeting | Ask for event date, outfit type, colour, budget and inspiration |
| Broadcasts | Past clients, prospects, graduation campaign, wedding season |

# 7. Campaign plan

| Campaign | Offer | Execution |
| --- | --- | --- |
| Graduated Designer, Dressing Graduates | Graduation dresses from M650 | Use her graduation story, friends discount, photographer partners |
| Never Basic at a Wedding | Wedding guest dresses from M850 | Reels, client proof, wedding season countdowns |
| Sunday Best Elegance | Church/event outfits | Monthly drop before salary weekends |
| Corporate Woman Capsule | 3-piece workwear capsule | Target banks, telecoms, NGOs, government and universities |

# 8. Partnership playbook

| Partner | Action | Commission |
| --- | --- | --- |
| Photographers | Refer graduation/event clients | 5-10% on paid deposits |
| Makeup artists | Dress + makeup bundle | 5-10% on paid deposits |
| Salons | Display lookbook / QR card | Referral incentive |
| Wedding planners | Bridal party package | 5-10% on paid deposits |
| Universities | Student ambassador or pop-up | Discount or commission |
| Women groups | Showcase church/corporate line | Group discount |

# 9. Operations and quality control

| Control area | Standard |
| --- | --- |
| Capacity | Define weekly slots for simple, premium, group and rush orders |
| Order control | No cutting without deposit and signed order form |
| Fitting | Book fitting date at deposit stage |
| Quality gate | Fit, seams, lining, pressing, packaging and final photo |
| Admin | Separate inquiries/follow-ups from sewing work |
| Delivery | Balance paid before handover |

# 10. 90-day roadmap

| Phase | Focus | Deliverables |
| --- | --- | --- |
| Days 1-7 | Commercial reset | Brand bio, price guide, catalogue, WhatsApp setup, testimonials |
| Days 8-30 | First campaign | Graduation launch, ad test, referral partners, daily CTAs |
| Days 31-60 | Scale proof | Wedding campaign, influencers, pop-up, client testimonials |
| Days 61-90 | Systemise | Ready-to-wear drop, corporate capsule, production dashboard |

# 11. First 7-day checklist

Choose final brand name and bio

Create 5 signature designs

Publish price guide with “from” pricing

Set WhatsApp Business catalogue and quick replies

Collect 10 testimonials/photos

Post graduation campaign announcement

Contact 10 referral partners

Run first M300-M500 boosted post

Start inquiry / quote / deposit tracker

Hold first weekly KPI review

# 12. Weekly management routine

| Day | Routine |
| --- | --- |
| Monday | Review previous week: inquiries, quotes, deposits, delivery issues |
| Tuesday | Follow up all unpaid quotes |
| Wednesday | Post client proof or transformation |
| Thursday | Push price/package post |
| Friday | Campaign CTA and urgency post |
| Saturday | Collect testimonials and pickup photos |
| Sunday | Plan next week’s content and production schedule |